## Tasks
Task ID | Task Name | Bucket Name | Progress | Priority | Assigned To | Created By | Created Date | Start date | Due date | Is Recurring | Late | Completed Date | Completed By | Completed Checklist Items | Checklist Items | Labels | Description
-P83w__ft0i51jMWEBGP5MkADhVz | Conduct user testing | Done | Not started | Important |  | P.B.W.K.D.S PALLEBATHGALA it22304988 |  |  |  | false | false |  |  |  |  | Yellow
0tnHpTOD90WzD5korK-IZckAFC7W | Write final report including | Done | Completed | Medium | IDDAMALGODA R it22925336;PIYATHILAKA S T P D K it22352194;ABEYRATHNE W G H S it22369956;P.B.W.K.D.S PALLEBATHGALA it22304988 | PIYATHILAKA S T P D K it22352194 | 04/20/2026 | 04/20/2026 | 04/26/2026 | false | false | 04/30/2026 | PIYATHILAKA S T P D K it22352194
2KWo2euN6EmTzdshkUwMRckAFpAZ | Train SVM model | Done | Completed | Medium | P.B.W.K.D.S PALLEBATHGALA it22304988 | P.B.W.K.D.S PALLEBATHGALA it22304988 | 02/02/2026 | 02/02/2026 | 02/07/2026 | false | false | 04/30/2026 | P.B.W.K.D.S PALLEBATHGALA it22304988
3pO8WjWmfUq1X3dbJWJkz8kAC-Cq | Deploy RAG system (Docker, Chroma DB, API integration) | Done | Completed | Medium | PIYATHILAKA S T P D K it22352194 | PIYATHILAKA S T P D K it22352194 | 03/01/2026 | 03/01/2026 | 03/06/2026 | false | false | 04/30/2026 | PIYATHILAKA S T P D K it22352194
4BtJZsZATUqtPuC31cWfVMkADz8e | Design UI wireframes | Done | Completed | Medium | IDDAMALGODA R it22925336;PIYATHILAKA S T P D K it22352194;ABEYRATHNE W G H S it22369956;P.B.W.K.D.S PALLEBATHGALA it22304988 | P.B.W.K.D.S PALLEBATHGALA it22304988 | 11/19/2025 | 11/19/2025 | 11/23/2025 | false | false | 04/30/2026 | P.B.W.K.D.S PALLEBATHGALA it22304988
61JwoQJM7Uyc1TL8e3nMSMkAJaRj | Design system workflow | Done | Completed | Medium | IDDAMALGODA R it22925336;PIYATHILAKA S T P D K it22352194;ABEYRATHNE W G H S it22369956;P.B.W.K.D.S PALLEBATHGALA it22304988 | P.B.W.K.D.S PALLEBATHGALA it22304988 | 11/29/2025 | 11/29/2025 | 12/03/2025 | false | false | 04/30/2026 | P.B.W.K.D.S PALLEBATHGALA it22304988
68SMcVG1GEuhEDqFDnmLOMkADR3b | Deploy model to GCP | Done | Completed | Medium | P.B.W.K.D.S PALLEBATHGALA it22304988 | P.B.W.K.D.S PALLEBATHGALA it22304988 | 02/22/2026 | 02/22/2026 | 02/25/2026 | false | false | 04/30/2026 | P.B.W.K.D.S PALLEBATHGALA it22304988
6t_le0_czkudxrfb0Wd0y8kAMxnN | Set up development environment (Python, LangChain, Chroma DB) | Done | Completed | Medium | PIYATHILAKA S T P D K it22352194 | PIYATHILAKA S T P D K it22352194 | 01/05/2026 | 01/05/2026 | 01/08/2026 | false | false | 04/30/2026 | PIYATHILAKA S T P D K it22352194
7KYH4tpwQUm3CSevOioTzskAHbs0 | Prepare Q&A for proposal | Done | Completed | Medium | IDDAMALGODA R it22925336;PIYATHILAKA S T P D K it22352194;ABEYRATHNE W G H S it22369956;P.B.W.K.D.S PALLEBATHGALA it22304988 | P.B.W.K.D.S PALLEBATHGALA it22304988 | 09/29/2025 | 09/29/2025 | 10/01/2025 | false | false | 04/30/2026 | P.B.W.K.D.S PALLEBATHGALA it22304988
7x-XbeoLVUGwju7EsRYPI8kAE7Sj | Determine project scope | Todo | Not started | Medium |  | P.B.W.K.D.S PALLEBATHGALA it22304988 | 09/29/2025 |  |  | false | false |  |  | 0/2 | Define potential obstacles;Define goals | Pink
85UKvRTNIkaMTQIIVHumP8kAENO2 | Plan system architecture | Done | Completed | Medium | IDDAMALGODA R it22925336;PIYATHILAKA S T P D K it22352194;ABEYRATHNE W G H S it22369956;P.B.W.K.D.S PALLEBATHGALA it22304988 | P.B.W.K.D.S PALLEBATHGALA it22304988 | 11/05/2025 | 11/05/2025 | 11/09/2025 | false | false | 04/30/2026 | P.B.W.K.D.S PALLEBATHGALA it22304988
8ghtpmLF3EWDg-ELIErxqMkAIc1e | Initiation | Done | Completed | Medium |  | PIYATHILAKA S T P D K it22352194 | 11/05/2025 |  | 09/01/2025 | false | false | 04/30/2026 | PIYATHILAKA S T P D K it22352194 | 5/5 | Draft Project Proposal Document;Identify research problem;Preparfor Proposal Presentation Q&A;Submitted TAF form;Creat Proposal Presentation slides
A58EUyjxBkqqeNFe_5OAMMkAPgaD | Design system architecture diagram | Done | Completed | Medium | IDDAMALGODA R it22925336;PIYATHILAKA S T P D K it22352194;ABEYRATHNE W G H S it22369956;P.B.W.K.D.S PALLEBATHGALA it22304988 | P.B.W.K.D.S PALLEBATHGALA it22304988 | 11/10/2025 | 11/10/2025 | 11/14/2025 | false | false | 04/30/2026 | P.B.W.K.D.S PALLEBATHGALA it22304988
AxMfd523tEWnafNIu2Y6eMkANNzF | Test RAG system | Done | Completed | Medium | PIYATHILAKA S T P D K it22352194 | PIYATHILAKA S T P D K it22352194 | 02/25/2026 | 02/25/2026 | 02/28/2026 | false | false | 04/30/2026 | PIYATHILAKA S T P D K it22352194
B5nTChEpgUS6qVeNUxzEXskAGINZ | Implement real-time prediction | Done | Completed | Medium | P.B.W.K.D.S PALLEBATHGALA it22304988 | P.B.W.K.D.S PALLEBATHGALA it22304988 | 03/08/2026 | 03/08/2026 | 03/12/2026 | false | false | 04/30/2026 | P.B.W.K.D.S PALLEBATHGALA it22304988
BCacxOzkE0q19Hu6xY9OeMkAP3v3 | Conduct needs analysis | InProgress | Not started | Medium |  | P.B.W.K.D.S PALLEBATHGALA it22304988 | 03/08/2026 |  |  | false | false |  |  | 0/3 | Evaluate information;Collect information;Prepare for data gathering | Pink
E7Wc-JjV_E2KjPYQfMuMockAMX9u | Requirement analysis | Done | Completed | Medium | IDDAMALGODA R it22925336;PIYATHILAKA S T P D K it22352194;ABEYRATHNE W G H S it22369956;P.B.W.K.D.S PALLEBATHGALA it22304988 | P.B.W.K.D.S PALLEBATHGALA it22304988 | 10/19/2025 | 10/19/2025 | 10/23/2025 | false | false | 04/30/2026 | P.B.W.K.D.S PALLEBATHGALA it22304988
EPmsc_F74kG_jJhgLhjNa8kAOHRs | Final improvements | Done | Completed | Medium | IDDAMALGODA R it22925336;PIYATHILAKA S T P D K it22352194;ABEYRATHNE W G H S it22369956;P.B.W.K.D.S PALLEBATHGALA it22304988 | P.B.W.K.D.S PALLEBATHGALA it22304988 | 03/30/2026 | 03/30/2026 | 04/03/2026 | false | false | 04/30/2026 | P.B.W.K.D.S PALLEBATHGALA it22304988
FIufse89sE-jzsY33w_ELckAJLXM | Plan Firebase/database | Done | Completed | Medium | PIYATHILAKA S T P D K it22352194;ABEYRATHNE W G H S it22369956;P.B.W.K.D.S PALLEBATHGALA it22304988 | P.B.W.K.D.S PALLEBATHGALA it22304988 | 12/04/2025 | 12/04/2025 | 12/07/2025 | false | false | 04/30/2026 | P.B.W.K.D.S PALLEBATHGALA it22304988
HV0dltmpDUCmzxxZ8qsp1skAH5CX | Develop mobile app UI | Done | Completed | Medium | PIYATHILAKA S T P D K it22352194;ABEYRATHNE W G H S it22369956;P.B.W.K.D.S PALLEBATHGALA it22304988 | P.B.W.K.D.S PALLEBATHGALA it22304988 | 02/26/2026 | 02/26/2026 | 03/01/2026 | false | false | 04/30/2026 | P.B.W.K.D.S PALLEBATHGALA it22304988
ImV-TKw5ZkSll_al2ueIAskABOuf | Finalize research idea | Done | Completed | Medium | IDDAMALGODA R it22925336;PIYATHILAKA S T P D K it22352194;ABEYRATHNE W G H S it22369956;P.B.W.K.D.S PALLEBATHGALA it22304988 | P.B.W.K.D.S PALLEBATHGALA it22304988 | 09/10/2025 | 09/10/2025 | 09/14/2025 | false | false | 04/30/2026 | P.B.W.K.D.S PALLEBATHGALA it22304988
KUn7k20Igk-exJYXSkceEskAD5uK | Analyze existing systems | Done | Completed | Medium | IDDAMALGODA R it22925336;PIYATHILAKA S T P D K it22352194;ABEYRATHNE W G H S it22369956;P.B.W.K.D.S PALLEBATHGALA it22304988 | P.B.W.K.D.S PALLEBATHGALA it22304988 | 10/09/2025 | 10/09/2025 | 10/12/2025 | false | false | 04/30/2026 | P.B.W.K.D.S PALLEBATHGALA it22304988
LHQ1A6t4oUm0IO9cSw5_WskAE-mM | Collect user feedback | Done | Completed | Medium | IDDAMALGODA R it22925336;PIYATHILAKA S T P D K it22352194;ABEYRATHNE W G H S it22369956;P.B.W.K.D.S PALLEBATHGALA it22304988 | P.B.W.K.D.S PALLEBATHGALA it22304988 | 03/26/2026 | 03/26/2026 | 03/29/2026 | false | false | 04/30/2026 | P.B.W.K.D.S PALLEBATHGALA it22304988
LhsIwDOIGU-KgKfvgDoe0MkAGYzX | Hyperparameter tuning | Done | Completed | Medium | P.B.W.K.D.S PALLEBATHGALA it22304988 | P.B.W.K.D.S PALLEBATHGALA it22304988 | 02/08/2026 | 02/08/2026 | 02/12/2026 | false | false | 04/30/2026 | P.B.W.K.D.S PALLEBATHGALA it22304988
M8otBnUtwUCwRh4el6UIdMkAA1GF | Identify research problem | Done | Completed | Medium | IDDAMALGODA R it22925336;PIYATHILAKA S T P D K it22352194;ABEYRATHNE W G H S it22369956;P.B.W.K.D.S PALLEBATHGALA it22304988 | P.B.W.K.D.S PALLEBATHGALA it22304988 | 09/01/2025 | 09/01/2025 | 09/03/2025 | false | false | 04/30/2026 | P.B.W.K.D.S PALLEBATHGALA it22304988
MSCzlCfvWkmpCk5Ed_2yH8kAICgP | Continue literature review | Done | Completed | Medium | IDDAMALGODA R it22925336;PIYATHILAKA S T P D K it22352194;ABEYRATHNE W G H S it22369956;P.B.W.K.D.S PALLEBATHGALA it22304988 | P.B.W.K.D.S PALLEBATHGALA it22304988 | 10/13/2025 | 10/13/2025 | 10/18/2025 | false | false | 04/30/2026 | P.B.W.K.D.S PALLEBATHGALA it22304988
MuOR5DTx8EypHRy-pbja3ckAFgKh | Develop backend API | Done | Completed | Medium | P.B.W.K.D.S PALLEBATHGALA it22304988 | P.B.W.K.D.S PALLEBATHGALA it22304988 | 02/16/2026 | 02/16/2026 | 02/21/2026 | false | false | 04/30/2026 | P.B.W.K.D.S PALLEBATHGALA it22304988
OLjDtR4V4Uev6yyUmnx7zskAIkj6 | Draft preliminary software specifications | InProgress | Not started | Medium |  | P.B.W.K.D.S PALLEBATHGALA it22304988 | 02/16/2026 |  |  | false | false |  |  |  |  | Pink
OWhBFm_vOkCDqGIXCOM6fMkAPi14 | Integrate frontend + backend | Done | Completed | Medium | PIYATHILAKA S T P D K it22352194;ABEYRATHNE W G H S it22369956;P.B.W.K.D.S PALLEBATHGALA it22304988 | P.B.W.K.D.S PALLEBATHGALA it22304988 | 03/02/2026 | 03/02/2026 | 03/07/2026 | false | false | 04/30/2026 | P.B.W.K.D.S PALLEBATHGALA it22304988
TiBEFwnAO0ueynkleriQ2ckAMyFx | Extract MFCC features | Done | Completed | Medium | P.B.W.K.D.S PALLEBATHGALA it22304988 | P.B.W.K.D.S PALLEBATHGALA it22304988 | 01/19/2026 | 01/19/2026 | 01/24/2026 | false | false | 04/30/2026 | P.B.W.K.D.S PALLEBATHGALA it22304988
TrtT5l2g0kOOfQv4ncBLkMkALWeE | Evaluate model accuracy | Done | Completed | Medium | P.B.W.K.D.S PALLEBATHGALA it22304988 | P.B.W.K.D.S PALLEBATHGALA it22304988 | 02/13/2026 | 02/13/2026 | 02/15/2026 | false | false | 04/30/2026 | P.B.W.K.D.S PALLEBATHGALA it22304988
YENl0T2YrEmQIfC9f8ZnqMkAGWhI | Submit research paper to conference | Done | Completed | Medium | IDDAMALGODA R it22925336;PIYATHILAKA S T P D K it22352194;ABEYRATHNE W G H S it22369956;P.B.W.K.D.S PALLEBATHGALA it22304988 | PIYATHILAKA S T P D K it22352194 | 03/16/2026 | 03/16/2026 | 03/30/2026 | false | false | 04/30/2026 | PIYATHILAKA S T P D K it22352194
ZKg8Cja4i0SWzBA5xrgTbMkAIfZ6 | Conduct literature review (start) | Done | Completed | Medium | IDDAMALGODA R it22925336;PIYATHILAKA S T P D K it22352194;ABEYRATHNE W G H S it22369956;P.B.W.K.D.S PALLEBATHGALA it22304988 | P.B.W.K.D.S PALLEBATHGALA it22304988 | 10/02/2025 | 10/02/2025 | 10/08/2025 | false | false | 04/30/2026 | P.B.W.K.D.S PALLEBATHGALA it22304988
ZW3XaMyxU0GzqrVburHbsMkANeX7 | Generate embeddings using multilingual-e5-large model and store in Chroma DB | Done | Completed | Medium | PIYATHILAKA S T P D K it22352194 | PIYATHILAKA S T P D K it22352194 | 04/20/2026 | 04/20/2026 | 04/22/2026 | false | false | 04/30/2026 | PIYATHILAKA S T P D K it22352194
_PmVAXxcr0aUD6_nbPwTJckAAOyl | Segment audio samples | Done | Completed | Medium | IDDAMALGODA R it22925336;PIYATHILAKA S T P D K it22352194;P.B.W.K.D.S PALLEBATHGALA it22304988 | P.B.W.K.D.S PALLEBATHGALA it22304988 | 01/11/2026 | 01/11/2026 | 01/15/2026 | false | false | 04/30/2026 | P.B.W.K.D.S PALLEBATHGALA it22304988
asAj4Njo6k6vZCE43H3UNskADlpc | Create use case diagram | Done | Completed | Medium | IDDAMALGODA R it22925336;PIYATHILAKA S T P D K it22352194;ABEYRATHNE W G H S it22369956;P.B.W.K.D.S PALLEBATHGALA it22304988 | P.B.W.K.D.S PALLEBATHGALA it22304988 | 11/15/2025 | 11/15/2025 | 11/18/2025 | false | false | 04/30/2026 | P.B.W.K.D.S PALLEBATHGALA it22304988
atLATi-zjEeIm7sXVWPTRckAMPrQ | Start SVM model | Done | Completed | Medium | P.B.W.K.D.S PALLEBATHGALA it22304988 | P.B.W.K.D.S PALLEBATHGALA it22304988 | 01/29/2026 | 01/29/2026 | 02/01/2026 | false | false | 04/30/2026 | P.B.W.K.D.S PALLEBATHGALA it22304988
cBm6bsIeEkW3z8lmOflk3skADKFS | Record audio samples | Done | Completed | Medium | IDDAMALGODA R it22925336;PIYATHILAKA S T P D K it22352194;ABEYRATHNE W G H S it22369956;P.B.W.K.D.S PALLEBATHGALA it22304988 | P.B.W.K.D.S PALLEBATHGALA it22304988 | 12/30/2025 | 12/30/2025 | 01/02/2026 | false | false | 04/30/2026 | P.B.W.K.D.S PALLEBATHGALA it22304988
cTYAsfCpi0Kwgwm7vt3UTMkAA9es | Write final report | Done | Completed | Medium | IDDAMALGODA R it22925336;PIYATHILAKA S T P D K it22352194;ABEYRATHNE W G H S it22369956;P.B.W.K.D.S PALLEBATHGALA it22304988 | P.B.W.K.D.S PALLEBATHGALA it22304988 | 04/04/2026 | 04/04/2026 | 04/08/2026 | false | false | 04/30/2026 | P.B.W.K.D.S PALLEBATHGALA it22304988
d69q_0anYEu2nzmRQ0exRckAJc94 | Supervisor review | Done | Completed | Medium | IDDAMALGODA R it22925336;PIYATHILAKA S T P D K it22352194;ABEYRATHNE W G H S it22369956;P.B.W.K.D.S PALLEBATHGALA it22304988 | P.B.W.K.D.S PALLEBATHGALA it22304988 | 12/18/2025 | 12/18/2025 | 12/21/2025 | false | false | 04/30/2026 | P.B.W.K.D.S PALLEBATHGALA it22304988
dRxftkK84E2AdnaqfODzZMkAPFnz | Build PDF ingestion pipeline | Done | Completed | Medium | PIYATHILAKA S T P D K it22352194 | PIYATHILAKA S T P D K it22352194 | 01/10/2026 | 01/10/2026 | 01/20/2026 | false | false | 04/30/2026 | PIYATHILAKA S T P D K it22352194
e97RVXYniEy_WWPl3QRng8kADVzc | Performance evaluation | Done | Completed | Medium | P.B.W.K.D.S PALLEBATHGALA it22304988 | P.B.W.K.D.S PALLEBATHGALA it22304988 | 03/21/2026 | 03/21/2026 | 03/25/2026 | false | false | 04/30/2026 | P.B.W.K.D.S PALLEBATHGALA it22304988
eZT8MzTNRkm-_B0WJ_-NI8kAMPpF | Integrate child session database (therapy progress, error patterns) with retrieved chunks | Done | Completed | Medium | PIYATHILAKA S T P D K it22352194 | PIYATHILAKA S T P D K it22352194 | 01/21/2026 | 01/21/2026 | 04/27/2026 | false | false | 04/30/2026 | PIYATHILAKA S T P D K it22352194
e_x2aX-wMEG08NAgYAhQv8kAFzJU | Define project scope (FR3) | Done | Completed | Medium | IDDAMALGODA R it22925336;PIYATHILAKA S T P D K it22352194;ABEYRATHNE W G H S it22369956;P.B.W.K.D.S PALLEBATHGALA it22304988 | P.B.W.K.D.S PALLEBATHGALA it22304988 | 09/04/2025 | 09/04/2025 | 09/06/2025 | false | false | 04/30/2026 | P.B.W.K.D.S PALLEBATHGALA it22304988
ggM81LBcPkiXgrKwj3aIW8kAOfBj | Build parent query interface and response display | Done | Completed | Medium | PIYATHILAKA S T P D K it22352194 | PIYATHILAKA S T P D K it22352194 | 02/10/2026 | 02/10/2026 | 02/15/2026 | false | false | 04/30/2026 | PIYATHILAKA S T P D K it22352194
h5sx8BuSoEGr2UiOYoK1hckADSef | Prepare dataset | Done | Completed | Medium | IDDAMALGODA R it22925336;PIYATHILAKA S T P D K it22352194;ABEYRATHNE W G H S it22369956;P.B.W.K.D.S PALLEBATHGALA it22304988 | P.B.W.K.D.S PALLEBATHGALA it22304988 | 01/25/2026 | 01/25/2026 | 01/28/2026 | false | false | 04/30/2026 | P.B.W.K.D.S PALLEBATHGALA it22304988
hRi5F5YiYUWsscKxRLscqskAKdce | Initial discussion with supervisor | Done | Completed | Medium | IDDAMALGODA R it22925336;PIYATHILAKA S T P D K it22352194;ABEYRATHNE W G H S it22369956;P.B.W.K.D.S PALLEBATHGALA it22304988 | P.B.W.K.D.S PALLEBATHGALA it22304988 | 09/07/2025 | 09/07/2025 | 09/09/2025 | false | false | 04/30/2026 | P.B.W.K.D.S PALLEBATHGALA it22304988
i8yGoKY1pEi3INZLyY-cc8kAFa1h | Prepare presentation | Done | Completed | Medium | IDDAMALGODA R it22925336;PIYATHILAKA S T P D K it22352194;ABEYRATHNE W G H S it22369956;P.B.W.K.D.S PALLEBATHGALA it22304988 | P.B.W.K.D.S PALLEBATHGALA it22304988 | 04/09/2026 | 04/09/2026 | 04/11/2026 | false | false | 04/30/2026 | P.B.W.K.D.S PALLEBATHGALA it22304988
ipcoyHPOE0m7VdM_ykq_kskAPiPM | Prepare design documentation | Done | Completed | Medium | IDDAMALGODA R it22925336;PIYATHILAKA S T P D K it22352194;ABEYRATHNE W G H S it22369956;P.B.W.K.D.S PALLEBATHGALA it22304988 | P.B.W.K.D.S PALLEBATHGALA it22304988 | 12/13/2025 | 12/13/2025 | 12/17/2025 | false | false | 04/30/2026 | P.B.W.K.D.S PALLEBATHGALA it22304988
jy1Fe4DVNUKfhup0IiCG-MkAHkN8 | Define SVM model approach | Done | Completed | Medium | P.B.W.K.D.S PALLEBATHGALA it22304988 | P.B.W.K.D.S PALLEBATHGALA it22304988 | 12/13/2025 |  | 11/04/2025 | false | false | 04/30/2026 | P.B.W.K.D.S PALLEBATHGALA it22304988
klF1SRG8lkSlI8pevVmZ7skABztZ | System testing | Done | Completed | Medium | P.B.W.K.D.S PALLEBATHGALA it22304988 | P.B.W.K.D.S PALLEBATHGALA it22304988 | 03/16/2026 | 03/16/2026 | 03/20/2026 | false | false | 04/30/2026 | P.B.W.K.D.S PALLEBATHGALA it22304988
lXvnc6qPWkmstIUxOyZ1hMkAOk8d | Develop prototype based on specifications | Done | Not started | Medium |  | P.B.W.K.D.S PALLEBATHGALA it22304988 | 03/16/2026 |  |  | false | false |  |  |  |  | Yellow
npGJYlU7Pku9dK6_wXkS48kAPlNn | Preprocessing (Audacity) | Done | Completed | Medium | PIYATHILAKA S T P D K it22352194;ABEYRATHNE W G H S it22369956;P.B.W.K.D.S PALLEBATHGALA it22304988 | P.B.W.K.D.S PALLEBATHGALA it22304988 | 01/05/2026 | 01/05/2026 | 01/10/2026 | false | false | 04/30/2026 | P.B.W.K.D.S PALLEBATHGALA it22304988
pSV7ePjIuUKI4JCf4SoiAMkAG9du | Design UI mockups | Done | Completed | Medium | IDDAMALGODA R it22925336;PIYATHILAKA S T P D K it22352194;ABEYRATHNE W G H S it22369956;P.B.W.K.D.S PALLEBATHGALA it22304988 | P.B.W.K.D.S PALLEBATHGALA it22304988 | 11/24/2025 | 11/24/2025 | 11/28/2025 | false | false | 04/30/2026 | P.B.W.K.D.S PALLEBATHGALA it22304988
qLXYOGeweEu3EpLKrTkHp8kAP9Rf | Develop code | Blocked | Not started | Medium |  | P.B.W.K.D.S PALLEBATHGALA it22304988 | 11/24/2025 |  |  | false | false |  |  |  |  | Green
qMuTSBc-2kK9b_MmsHCb_MkADgbF | Implement therapist knowledge base management (upload, rename, delete files with auto re-indexing) | Done | Completed | Medium | PIYATHILAKA S T P D K it22352194 | PIYATHILAKA S T P D K it22352194 | 02/15/2026 | 02/15/2026 | 02/25/2026 | false | false | 04/30/2026 | PIYATHILAKA S T P D K it22352194
sPiRMWiCb0WL0Is-7ZjcTckAD4_G | Organize dataset | Done | Completed | Medium | IDDAMALGODA R it22925336;PIYATHILAKA S T P D K it22352194;ABEYRATHNE W G H S it22369956;P.B.W.K.D.S PALLEBATHGALA it22304988 | P.B.W.K.D.S PALLEBATHGALA it22304988 | 01/03/2026 | 01/03/2026 | 01/04/2026 | false | false | 04/30/2026 | P.B.W.K.D.S PALLEBATHGALA it22304988
t1tyCAbfBEe-w0QwPFsYdskALCBk | Collect speech data | Done | Completed | Medium | IDDAMALGODA R it22925336;PIYATHILAKA S T P D K it22352194;ABEYRATHNE W G H S it22369956;P.B.W.K.D.S PALLEBATHGALA it22304988 | P.B.W.K.D.S PALLEBATHGALA it22304988 | 12/22/2025 | 12/22/2025 | 12/29/2025 | false | false | 04/30/2026 | P.B.W.K.D.S PALLEBATHGALA it22304988
tLVZXOJWhEqpyRjx5AuG4ckAOZW3 | Unit testing | Done | Completed | Medium | P.B.W.K.D.S PALLEBATHGALA it22304988 | P.B.W.K.D.S PALLEBATHGALA it22304988 | 03/13/2026 | 03/13/2026 | 03/15/2026 | false | false | 04/30/2026 | P.B.W.K.D.S PALLEBATHGALA it22304988
uc3qv6_mLU6TZ8TAXM1pPMkAO7DQ | Label dataset | Done | Completed | Medium | PIYATHILAKA S T P D K it22352194;ABEYRATHNE W G H S it22369956;P.B.W.K.D.S PALLEBATHGALA it22304988 | P.B.W.K.D.S PALLEBATHGALA it22304988 | 01/16/2026 | 01/16/2026 | 01/18/2026 | false | false | 04/30/2026 | P.B.W.K.D.S PALLEBATHGALA it22304988
v7fH3Su0Nkq6NnAQDblkdMkAB0iS | Write research paper | Done | Completed | Medium | IDDAMALGODA R it22925336;PIYATHILAKA S T P D K it22352194;ABEYRATHNE W G H S it22369956;P.B.W.K.D.S PALLEBATHGALA it22304988 | PIYATHILAKA S T P D K it22352194 | 02/01/2026 | 02/01/2026 | 03/15/2026 | false | false | 04/30/2026 | PIYATHILAKA S T P D K it22352194
xNBiGfS14EyFVZ6bYgBJWckAEs2e | Create Gantt / Planner | Done | Completed | Medium | IDDAMALGODA R it22925336;PIYATHILAKA S T P D K it22352194;ABEYRATHNE W G H S it22369956;P.B.W.K.D.S PALLEBATHGALA it22304988 | P.B.W.K.D.S PALLEBATHGALA it22304988 | 10/27/2025 | 10/27/2025 | 10/30/2025 | false | false | 04/30/2026 | P.B.W.K.D.S PALLEBATHGALA it22304988
yBfspISRUEqwuRnlrGNNiskAKn9U | Planning | Done | Not started | Medium |  | PIYATHILAKA S T P D K it22352194 | 10/27/2025 |  | 10/16/2025 | false | true |  |  | 2/5 | Perform requirement analysis;Create project schedule;Collect fatigue-related dataset;Conduct literature review;Define RAG model objectives
yBjN4JjxU06CqzsZGCYVa8kALByW | Finalize system design | Done | Completed | Medium | IDDAMALGODA R it22925336;PIYATHILAKA S T P D K it22352194;ABEYRATHNE W G H S it22369956;P.B.W.K.D.S PALLEBATHGALA it22304988 | P.B.W.K.D.S PALLEBATHGALA it22304988 | 12/08/2025 | 12/08/2025 | 12/12/2025 | false | false | 04/30/2026 | P.B.W.K.D.S PALLEBATHGALA it22304988
yEvezhvBikCsIyi4w8i5J8kAChp9 | Identify dataset sources | Done | Completed | Medium | IDDAMALGODA R it22925336;PIYATHILAKA S T P D K it22352194;ABEYRATHNE W G H S it22369956;P.B.W.K.D.S PALLEBATHGALA it22304988 | P.B.W.K.D.S PALLEBATHGALA it22304988 | 10/24/2025 | 10/24/2025 | 10/26/2025 | false | false | 04/30/2026 | P.B.W.K.D.S PALLEBATHGALA it22304988
IshPeaFQt0aUijTYbWm2l8kAALzT | Design phoneme error input handling and therapist prompt format | Done | Completed | Medium | ABEYRATHNE W G H S it22369956 | ABEYRATHNE W G H S it22369956 | 10/09/2025 | 10/09/2025 | 10/12/2025 | false | false | 04/30/2026 | ABEYRATHNE W G H S it22369956
6PyrPabJXECvdh7aNs__WckAPvce | Data Pre Processing in sinhala Voice Clone | Done | Completed | Medium | IDDAMALGODA R it22925336 | IDDAMALGODA R it22925336 | 10/09/2025 |  |  | false | false | 04/30/2026 | IDDAMALGODA R it22925336
jor5xFRo3EWMr3Kz2OB2zckAInfM | Ready DS for proper algorithm | Done | Completed | Medium | IDDAMALGODA R it22925336 | IDDAMALGODA R it22925336 | 10/09/2025 | 10/09/2025 | 10/23/2025 | false | false | 04/30/2026 | IDDAMALGODA R it22925336
7_cGxWTG6kSMhTKa2s53kckANuM1 | Model Training for Cuqui TTS | Done | Completed | Medium | IDDAMALGODA R it22925336 | IDDAMALGODA R it22925336 | 10/09/2025 |  | 11/03/2025 | false | false | 04/30/2026 | IDDAMALGODA R it22925336
Kqh6ugbwFkGy9ys8QyUdHckAIHTn | Fixing Model Training | Done | Completed | Medium | IDDAMALGODA R it22925336 | IDDAMALGODA R it22925336 | 10/09/2025 |  | 11/17/2025 | false | false | 04/30/2026 | IDDAMALGODA R it22925336
2XTaWHbaSEq2a03WEJtXPMkAPD9A | Develop rule-based therapy generation engine with phoneme-to-activity mapping | Done | Completed | Medium | ABEYRATHNE W G H S it22369956 | ABEYRATHNE W G H S it22369956 | 10/13/2025 | 10/13/2025 | 10/18/2025 | false | false | 04/30/2026 | ABEYRATHNE W G H S it22369956
HlcyzEdCPU6ns0qkFMTm6skANBOk | Integrate Sinhala phonology knowledge graph with therapy generation logic | Done | Completed | Medium | ABEYRATHNE W G H S it22369956 | ABEYRATHNE W G H S it22369956 | 10/19/2025 | 10/19/2025 | 10/23/2025 | false | false | 04/30/2026 | ABEYRATHNE W G H S it22369956
1_ja1EWGlU6505ml3vGJmMkAJPfm | Build indexed search mechanism for accurate therapy retrieval | Done | Completed | Medium | ABEYRATHNE W G H S it22369956 | ABEYRATHNE W G H S it22369956 | 10/24/2025 | 10/24/2025 | 10/26/2025 | false | false | 04/30/2026 | ABEYRATHNE W G H S it22369956
tVSIw5e7aEeQQydQpRL5uMkAFawm | Implement therapy generation pipeline (input → processing → structured output) | Done | Completed | Medium | ABEYRATHNE W G H S it22369956 | ABEYRATHNE W G H S it22369956 | 10/27/2025 | 10/27/2025 | 10/30/2025 | false | false | 04/30/2026 | ABEYRATHNE W G H S it22369956
1pRz-2M6bUKAB8vreBuaRMkAB_M2 | Develop therapy validation, feedback handling, and quality checking system | Done | Completed | Medium | ABEYRATHNE W G H S it22369956 | ABEYRATHNE W G H S it22369956 | 11/05/2025 | 11/05/2025 | 11/09/2025 | false | false | 04/30/2026 | ABEYRATHNE W G H S it22369956
jmr0pn7o806sl-sUjtHFNMkABtdC | Design & build therapy generation logic (rules + knowledge graph) | Done | Completed | Medium | ABEYRATHNE W G H S it22369956 | ABEYRATHNE W G H S it22369956 | 11/09/2025 | 11/09/2025 | 12/10/2025 | false | false | 04/30/2026 | ABEYRATHNE W G H S it22369956
Y-hZPBojv0i6wQjblNxO-MkALMv1 | Implement therapy validation and feedback handling | Done | Completed | Medium | ABEYRATHNE W G H S it22369956 | ABEYRATHNE W G H S it22369956 | 12/11/2025 | 12/11/2025 | 01/15/2026 | false | false | 04/30/2026 | ABEYRATHNE W G H S it22369956
61U0BMR9i0GdRNIqNHPm4skAG1S0 | Develop therapy material generation and integrate Sinhala TTS | Done | Completed | Medium | ABEYRATHNE W G H S it22369956 | ABEYRATHNE W G H S it22369956 | 01/16/2026 | 01/16/2026 | 01/31/2026 | false | false | 04/30/2026 | ABEYRATHNE W G H S it22369956
XGEihCmZqEGRK6ZyZECv_ckAFiaO | Create therapy packaging, adaptive learning, and progress tracking | Done | Completed | Medium | ABEYRATHNE W G H S it22369956 | ABEYRATHNE W G H S it22369956 | 02/01/2026 | 02/01/2026 | 02/28/2026 | false | false | 04/30/2026 | ABEYRATHNE W G H S it22369956
IA4xKUHT8E6cQTQ-4KnOgskAJziz | Integrate therapy module with system and finalize optimization | Done | Completed | Medium | ABEYRATHNE W G H S it22369956 | ABEYRATHNE W G H S it22369956 | 03/01/2026 | 03/01/2026 | 03/07/2026 | false | false | 04/30/2026 | ABEYRATHNE W G H S it22369956
r5MlSPFauEid4KVM6_Un1skACuX6 | Prototype Electronics in Toy Robot | Todo | Completed | Medium | IDDAMALGODA R it22925336 | IDDAMALGODA R it22925336 | 12/01/2025 | 12/01/2025 | 12/07/2025 | false | false | 04/30/2026 | IDDAMALGODA R it22925336
Wz8JLlgMz0SxVHxiIcCCqskAHFeB | 3D Modling Robot Design | Todo | Completed | Medium | IDDAMALGODA R it22925336 | IDDAMALGODA R it22925336 | 12/01/2025 |  | 12/21/2025 | false | false | 04/30/2026 | IDDAMALGODA R it22925336
L_f8xtZvoEW5UAlafPubjskALYlW | Start Basic electronic Design in Raspberry pi | Todo | Completed | Medium | IDDAMALGODA R it22925336 | IDDAMALGODA R it22925336 | 12/01/2025 |  | 12/28/2025 | false | false | 04/30/2026 | IDDAMALGODA R it22925336
kV28kbrw7Uec85GlCdIF8ckAHN_S | Completing 50% Prototype | Todo | Completed | Medium | IDDAMALGODA R it22925336 | IDDAMALGODA R it22925336 | 12/29/2025 | 12/29/2025 | 01/03/2026 | false | false | 04/30/2026 | IDDAMALGODA R it22925336
aQb8vYNIWEie3dTbbEfed8kAAOyz | Fine Tuning Model | Todo | Completed | Medium | IDDAMALGODA R it22925336 | IDDAMALGODA R it22925336 | 01/05/2026 | 01/05/2026 | 01/18/2026 | false | false | 04/30/2026 | IDDAMALGODA R it22925336
Kmw9gxFKT0qxFVeAnmBPHskAMm5C | Design robot motor functions | Todo | Completed | Medium | IDDAMALGODA R it22925336 | IDDAMALGODA R it22925336 | 01/12/2026 | 01/12/2026 | 01/25/2026 | false | false | 04/30/2026 | IDDAMALGODA R it22925336
EotRpD68j0iZvDPBStJ6JskAAZHO | Fine tune robot design in raspberry pi | Todo | Completed | Medium | IDDAMALGODA R it22925336 | IDDAMALGODA R it22925336 | 01/12/2026 |  |  | false | false | 04/30/2026 | IDDAMALGODA R it22925336
yScDFx36ukCljazO_TtaVskAMfzO | Ready Robot for 90% Progress | Todo | Completed | Medium | IDDAMALGODA R it22925336 | IDDAMALGODA R it22925336 | 01/12/2026 |  | 02/26/2026 | false | false | 04/30/2026 | IDDAMALGODA R it22925336
FmyrPqdgOEymYyoxqGPblckAMI_c | Fine tune Model for final evaluation | Todo | Completed | Medium | IDDAMALGODA R it22925336 | IDDAMALGODA R it22925336 | 01/12/2026 |  | 03/31/2026 | false | false | 04/30/2026 | IDDAMALGODA R it22925336
lUebQICdgUOL6dyeugzFEckAAY9- | Finalyze 3D model for optimize in design | Todo | Completed | Medium | IDDAMALGODA R it22925336 | IDDAMALGODA R it22925336 | 01/12/2026 |  | 04/12/2026 | false | false | 04/30/2026 | IDDAMALGODA R it22925336

## Plan name
Plan name | HURUWA
Plan ID | IBqAiG60NUyjYrmfgDMjy8kADf25
Date of export | 04/30/2026